## Change History
Date | Description | Author
2016-06-21 | UDW BA Work Breakdown Structure Tasklist | Lisa Cunningham
2016-06-23 | Updated information regarding the Semantic View sections | Lisa Cunningham
2016-06-29 | Added two MRR Reference documents from Libby Mathai: *UDW MRR Standard Work Package *Standards for UDW Referenct Table Design | Lisa Cunningham
2016-06-30 | Update Task 79 with Note regarding Metadata Repository | Lisa Cunningham
2016-07-11 | Added document 'Guidelines for metadata definitions' by Laura Sebastian-Coleman | Lisa Cunningham
2016-07-14 | Added some additional documents around creating Data Dictionary Definitions on Task 130 and to the Referenced Documents Tab | Lisa Cunningham
2016-07-27 | Added Tasks 71 - 73 for the Model Simplification information. | Lisa Cunningham
2015-08-15 | Added Task E - regarding changes to the SIT environment - BA Team needs to be informed to see if there are impacts to other initiatives. | Lisa Cunningham
2016-10-07 | Removed the date from the title of the UDW BA Mapping - Standard Rules document, updated all references to this document | Lisa Cunningham
2016-10-17 | Updated Knowledge Tranfer information | Lisa Cunningham
2016-10-20 | Added the ImpactAnalysis Review Board Checklist document | Lisa Cunningham
2016-12-14 | Added document "BA Standards_Production Checkout" | Lisa Cunningham
2017-01-04 | Updated document locations that have been moved to the new BA Sharepoint | Lisa Cunningham
2017-01-05 | Added information on Global IDs which is a Profiling tool used for data in the Data Lake | Lisa Cunningham
2017-02-02 | Added information on the Metadata Repository Updates | Lisa Cunningham
2017-02-03 | Updated documentation links for Reference Data Management (MRR) | Lisa Cunningham
2017-04-03 | Updated Metadata Repository Section, Tasks 133 to 139 | Lisa Cunningham
2017-08-08 | Updated links that were not working. Added tasks for UDW End User Community Review. Added samples for UAT Deck and UDW End User Community Review. | Lisa Cunningham

## BA WBS Tasks
Agile Framework
Task # | Phase | Stage | Task | BA Role: R: Responsible A: Accountable C: Consulted I: Informed | Other involved Team Members Roles | Input Artifacts to the Phase | Output Artifact created or updated? | Artifact Template | Available Training Documentation | Sample Document | User Story Standard # (Polaris Team is working on these) | Spike Story (in scope but level of work unexpected)
A | Statement of Work (SOW) | BA Review and Validate | BAs will be consulted by the Business Engagement Team to provide input for an SOW: * Gain understanding of the Business Request * Review and provide clarification for the Requirements * Provide estimate of # of Tables/Attributes which will fulfill requirements. * Review overall BA estimate to ensure hours for BA work. | C | R: Business Engagement, Asset Leads | SPRF | N
B | Project Estimating | BA Estimating during Project Phases | Lead Project BA will be expected to provide input to a reassessment of the estimate as the project progresses through the phases. | C | R: Dev Team C: Project Mgr., Project Team |  | Y | Dev Template for Estimating
C | Project Support | BA Support | Lead BA and Project BAs will be working in colloboration and supporting all Project Disciplines throughout all project phases. | R | R: Project Team |  | N
D | QA Support | QA Collaboration | Work with QA Lead to ensure that specific business test cases are not missed in testing throughout all project phases. NOTE: BA will still perform BA checkout. | R | C: QA Lead |  | N
E | All Phases | All UDW Environments | When working on projects that are changing the test bed data in SIT, please send a communication out in advance, to the entire team to ensure changes will not impact other project/program deliverables. | R | C: Project Mgr., Project Team | N/A | Y | No Template - Email notification to entire BA Team
1 | Data Acquisition | Data Discovery and Staging | The goal of Business Analysis Data Discovery and Staging is to provide a thorough understanding of a source system’s processes and data. Staged data and documents are used in follow-on activities such as integration by business analysts, developers and quality analysts. If the project requirements can be filled by an existing source to UDW, you may only need to locate and update the existing documentation. |  |  | * Asset Component Inventories * Statement of Work * Copybooks w/layouts * Data flow diagram * Data Interface Technology Reqs * Data Model * Process flow diagram * Sharepoints * Source Data Dictionary * System flow / context diagram * System overview * Any other documents helpful to complete job | N/A |  | * Data Intake Staging Process * UDW BA Data Discovery and Staging Training
2 | Data Acquisition | Data Discovery and Staging | Review any documentation that is available at the start of the project. | R | R: Project Team | Statement of Work (SOW) | N/A
3 | Data Acquisition | Data Discovery and Staging | If this is for a new source, identify source system to meet requirements. NOTE: If this is for an existing source within UDW, look for documentation on the UDW Stage Specification Documents Sharepoint. | R | R: Solution Architect, Data Architect | * Application Systems Group Catalog (ASG) * Asset Component Inventories | N | Initial Data Sourcing Discussion Questions
4 | Data Acquisition | Data Discovery and Staging | Generate or update a Source Analysis Recommendation Document (SAR). | R | R: Solution Architect, Data Architect | Source Documentation | Y | Source Analysis Recommendation_Template |  | SAR_DA0182 BRMS Data Feeds to UDW_BRS
5 | Data Acquisition | Data Discovery and Staging | Review Source Analysis Recommendation Document (SAR) with the Project Team and make updates as applicable. | R | C: Project Team | Source Analysis Recommendation (SAR) | Y | Source Analysis Recommendation (SAR) - See Sample
6 | Data Acquisition | Data Discovery and Staging | Create SAR Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR and upload to Sharepoint. | R | A: Project Team |  | Y | Artifact Signoff Form (ASF) or ADR
7 | Data Acquisition | Data Discovery and Staging | Gather and review artifacts for the source, e.g., functional specifications and metadata. | R | I: Project Team | Source Documentation | N
8 | Data Acquisition | Data Discovery and Staging | Inspect data in legacy sources. NOTE: This task will require access to the Source System. | R | C: Source SME |  | N
9 | Data Acquisition | Data Discovery and Staging | Copy applicable reference documents to Project Sharepoint. | R |  | Source Documentation | N
10 | Data Acquisition | Data Discovery and Staging | Meet with Solution Architect to review approach to data discovery. | R | R: Solution Architect |  | N
11 | Data Acquisition | Interface Agreement | BA coordinates with Solution Architect on Interface Agreement preparation or update. | C | R: Solution Architect | Source Analysis Recommendation (SAR) | Y | Interface Agreement. See Sample | Interface Agreement Process | IA_4-68497_BRMS
12 | Data Acquisition | Interface Agreement | BA provides source table list, history acquisition business rules (selection criteria), volume estimates and other business rules as applicable for the Interface Agreement, if they do not already exist. | R | R: Solution Architect | Source Documentation | Y | Gathered Source Documentation
13 | Data Acquisition | Interface Agreement | BA will continue to provide support where needed for further updates to the Interface Agreement following solution approval and throughout the development lifecycle. | C | R: Solution Architect |  | N
14 | Data Acquisition | Attribute Gap Inventory | Identify requested attributes. | R | C: Business, Source SME | * Statement of Work (SOW) * Source Documentation | Y | Map & Gap Template |  | Map and Gap COSMOS to DSS_Med Claim and Encounters
15 | Data Acquisition | Attribute Gap Inventory | Perform Gap Analysis of requirements against source layouts. | R | C: Source SME | * Statement of Work (SOW) * Source Documentation | Y | Map & Gap Template
16 | Data Acquisition | Attribute Gap Inventory | Review Gap Analysis questions and results with Project Team, Business, and Source SMEs. | R | C: Project Team, Souce SME, Business | Map & Gap Analysis | Y | Map & Gap Template
17 | Data Acquisition | Attribute Gap Inventory | Obtain agreement on gaps or escalate to Strategic Guidance Council (SGC) or BVT (Business Value Team) as appropriate. | R | A: Source SME, Business | Map & Gap Analysis | Y | * Map & Gap Template * Submission Template for SGC Topics
18 | Data Acquisition | Attribute Gap Inventory | Identify possibilities of where Reference Codes/Descriptions may be needed in the Gap Analysis NOTE: Whether the Reference data follows an MRR vs. ETL process would be determined during Data Integration. | R | I: Project Team | Source Documentation | Y | Map & Gap Template
19 | Data Acquisition | Attribute Gap Inventory | Present acquistion issues and decisions to the Strategic Guidance Council (SGC). | R | C: Strategic Guidance Council | * Solution Analysis Results (SAR) *Business Requirements Document (BRD) * Gap Analysis | Y | Submission Template for SGC Topics
20 | Data Acquisition | Attribute Gap Inventory | Add any items deemed Out of Scope to the Tracker. | R | C: Strategic Guidance Council, Project Team | * Gap Analysis * SGC Presentation | Y | Master Out of Scope Tracking - after decision
21 | Data Acquisition | Attribute Gap Inventory | Create SGC Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR and upload to Sharepoint. | R | A: Strategic Guidance Council |  | Y | Artifact Signoff Form (ASF) or ADR
22 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Understand and document source system processes, data structures and how data changes over time, if this documentation does not already exist. | R | R: Source SME | Source Documentation | Y | Data Discovery Questionnaire (DDQ) | UDW Data Discovery Questionnaire Overview | DDQ_Revenue_ESB
23 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Review basic discovery questions template and update with additional questions based on the source and the data. If this Source already exists in UDW, review available discovery documents and add new information where necessary. | R | C: Project Team | Source Documentation | Y | Data Discovery Questionnaire (DDQ)
24 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Review lifecycle questions. If this Source already exists in UDW, review available discovery documents and add new information where necessary. | R | C: Project Team | Source Documentation | Y | Data Discovery Questionnaire (DDQ)
25 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Add or modify questions based on the source and domain, business requirements, gap analysis. | R | C: Project Team | Source Documentation | Y | Data Discovery Questionnaire (DDQ)
26 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Identify Project Team, Source and Business Participants for the Data Discovery Questionnaire sessions. | C | R: Project Mgr. C: ODM Program Mgmt, Business, Source Contacts |  | Y | No Template - Spreadsheet of identified Participants, Business Area, Role, etc.
27 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Conduct data discovery kick-off meeting. | R | R: Project Team, Business, Source SMEs | Data Discovery Questionnaire (DDQ) | Y | Data Discovery Questionnaire (DDQ)
28 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Request artifacts and references from source if they have not already been collected: * System overview * Data flow diagram * Process flow diagram * Data Model * System flow / context diagram * Data Dictionary (with table and field elements) * Copybooks with layouts * Any other documents helpful to complete job * Sharepoints NOTE: Any additional Source Artifacts obtained during the DDQ Sessions should be uploaded to the Project Sharepoint. | R | R: Source SMEs | Source Documentation | N
29 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Schedule meetings to review artifacts and interview participants. | I | R: Project Mgr. |  | N
30 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Publish minutes for each session. | R | C: DDQ Participants |  | Y | Meeting Minutes. See Sample |  | DDQ_CDB Data Discussions
31 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Probe on data lifecycles. | R | C: Project Team, Business, Source SMEs |  | Y | Data Discovery Questionnaire (DDQ)
32 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Update the DDQ to identify followup questions and contacts. | R | C: Project Team, Business, Source SMEs |  | Y | Data Discovery Questionnaire (DDQ)
33 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Document interview results in DDQ and associated documents. | R | C: Project Team, Business, Source SMEs |  | Y | Data Discovery Questionnaire (DDQ)
34 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | ReviewDDQ results summary with team. | R | I: Project Team, Business, Source SMEs |  | Y | Data Discovery Questionnaire (DDQ)
35 | Data Acquisition | Prepare and Complete Data Discovery Questionnaire | Create DDQ Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR and upload to Sharepoint. | R | A: Project Team, Business, Source SMEs |  | Y | Artifact Signoff Form (ASF) or ADR
36 | Data Acquisition | Data Lifecycle | Draft data lifecycle use cases. NOTE: Development of lifecycle use cases depends on the size and complexity of the project. | Optional |  |  | Y | Data Lifecycle Template | UDW Data Lifecycles | LC_Provider Demographics_NDB
37 | Data Acquisition | Data Lifecycle | Write narrative overview of source data behavior. The data lifecycle document is written throughout the project. | Optional | C: Project Team |  | Y | Data Lifecycle Template
38 | Data Acquisition | Data Lifecycle | Inspect or profile data in Teradata Environment or Data Lake. | Optional | C: Source SME | Source File, Domain Expectations, High Level DQ Expectations | N
39 | Data Acquisition | Data Lifecycle | Document primary and alternate data lifecycle scenarios. | Optional | C: Source SME |  | Y | Data Lifecycle Template
40 | Data Acquisition | Data Lifecycle | Add details to lifecycle use cases including deidentified data examples. | Optional | C: Source SME |  | Y | Data Lifecycle Template
41 | Data Acquisition | Data Lifecycle | Add key business rules that impact the data. | Optional | C: Source SME |  | Y | Data Lifecycle Template
42 | Data Acquisition | Data Lifecycle | Review with source system SMEs for correctness and completeness. | Optional | R: Souce SMEs |  | Y | Data Lifecycle Template
43 | Data Acquisition | Data Lifecycle | Review with Lead BA and Domain Leads. | Optional | R: Lead BA, Domain Leads |  | Y | Data Lifecycle Template
44 | Data Acquisition | Data Lifecycle | Save to Sharepoint and send link to the project team. | Optional | I: Project Team |  | Y | * Data Lifecycle Template * No template - Email notification
45 | Data Acquisition | Metadata Master | Obtain latest Metadata Master template or locate the existing document in the UDW Stage Specification Document Library Sharepoint. | R |  |  | Y | Metadata Master Template | MM Metadata Master Process | MM_CDB
46 | Data Acquisition | Metadata Master | Gather source system metadata: copybooks, data dictionaries, other references where applicable. | R | C: Source SME | Source Documentation | Y | Metadata Master Template
47 | Data Acquisition | Metadata Master | Complete table list for table or files in scope for staging. Include business name and definition. NOTE: All definitions MUST be provided by the Source. We do not want to have to make something up - Source definitions are important. If the Source does not have a definition they need to work with us to come up with an appropriate definition. | R |  | Source Documentation | Y | Metadata Master Template
48 | Data Acquisition | Metadata Master | Work with team to identify pattern and physical content description. | R | C: Project Team, Source SME | Source Documentation | Y | Metadata Master Template
49 | Data Acquisition | Metadata Master | Complete table layout with table/file name, elements, business name and definitions provided by source. Include Physical Characteristics and Position if available. | R | C: Project Team, Source SME | Source Documentation | Y | Metadata Master Template
50 | Data Acquisition | Metadata Master | Identify PHI and PII fields. | R | C: Project Team, Source SME | Source Documentation | Y | Metadata Master Template
51 | Data Acquisition | Metadata Master | Save to Sharepoint and send link to the project team so that the Metadata Master is available for Developer to build out the Target Tables. | R | I: Project Team | Source Documentation | Y | * Metadata Master Template * No template - Email notification
52 | Data Acquisition | Data Profiling | For Terradata submit a request for Information Analyzer profiling to the ETL Tech Resource to include: - Source - Table Name and Environment (UDWTST, UDWPROD) - Project initiative - Slicing Criteria - any criteria to be applied for profiling a specified subset of the data (ex: date ranges, provider types, etc…) NOTE: There will be another tool to use for Data Lake - when the process is available, it will be added to this spreadsheet. | R | C: Project Mgr., ETL Tech Resource | Source Documentation | Y | Profiling Request Tracking (Follow the steps on the 'Overview, Process' Tab) | * Data Profiling Overview * Info_Analyzer_-_Quick_Start_Guide, 051915 * IA-Redbook * InfoAnalyzer - Profiled Data Files
53 | Data Acquisition | Data Profiling | Perform high-level profiling of staged data. Review Info Analyzer results in brief focusing on following items: * Min/Max values * Null value counts * Default values and number of defaults * Cardinality and distinct values | R | C: Source SME | Source Data | Y | DataAnalysisResultsTEMPLATE V3.0 Data Analysis Results (DAR) |  | DAR_Provider_HHR
54 | Data Acquisition | Data Profiling | Copy Information Analyzer results into Data Analysis Results Excel. Note issues in the 'Observation List' worksheet and update status in the Data Analysis checklist. | R |  | Source Data | Y | DataAnalysisResultsTEMPLATE V3.0 Data Analysis Results (DAR)
55 | Data Acquisition | Data Profiling | Perform additional ad-hoc profiling to identify and understand data lifecycle examples. | R | C: Source SME | Source Data | Y | DataAnalysisResultsTEMPLATE V3.0 Data Analysis Results (DAR)
56 | Data Acquisition | Data Profiling | For profiling data in the Data Lake, Global IDs will be utilized. Please refer to BA Team Meetings 9/15/2016 and 9/29/2016 for further instruction | R | C: Project Mgr., ETL Tech Resource, Source SME | Source Documentation and Source Data | Y | Global IDs - Profiling Request Tracking | * BA Team Meeting 9/15/2016 * BA Team Meeting 9/29/2016 * Global IDs - Quick_Start_Guide * Global IDs - Tips and Tricks
57 | Data Acquisition | Deployment Checkout Testing | Document BA deployment checkout test cases for the build out of the Source data to the Target (i.e., UDW Stage) - these should complement the QA check-out testing. | R | I: Quality Assurance |  | Y | Document BA Test Cases and Expected Results. See Sample |  | 3RDD_HHS_Extract_RXClaim_Iteration_Test_Cases
58 | Data Acquisition | Deployment Checkout Testing | Perform BA checkout testing of the Source data to the UDW Target. | R |  | BA Test Case document | Y | Record Pass/Fail of the BA Test Cases.
59 | Data Acquisition | Deployment Checkout Testing | Report any issues, if identified: * update required documents * review with the project team for approval/signoff * retest | R | I: Project Team |  | Y | * Enter ALM Tickets * Update Project Artifacts where applicable
60 | Data Integration | Business Requirements Analysis for Data Integration | The Goal of the Data Integration Phase is to bring in the Source data from UDW Stage, store and integrate it with existing UDW Base Data, enrich the data where necessary and make it available to the UDW End User. This may also require bringing in additional data from an existing Source through UDW Stage to Base, creating Semantic Views to fulfill specific customer reporting requirements and publishing data extracts to specific data Clients. |  |  |  | N/A
61 | Data Integration | Documentation Review | Review Data Acquisition Documention in preparation for Data Integration Tasks. | R | R: Project Team | * Source Analysis Recommendation * Interface Agreement * Data Discovery Questionnaire (DDQ) * Source Metadata Master (MM) * Lifecycle Document (LC) * Data Anlysis Results (DAR) * Existing Data Models * UDW Stage Mappings * UDW Base Mappings * PubSub Mappings * Program Requirements Document (PRD) | N
62 | Data Integration | Business Requirements Documents Creation | Create Business Requirements Document (BRD) What about an RTM? | R |  | * Statement of Work (SOW) * Program Requirements Document | Y | Business Requirements Document (BRD) |  | BRD_4-68460 - VBC Measurement Enhancements
63 | Data Integration | Business Requirements Documents Creation | Review the BRD with the Project Team and with Business. Make updates as appropriate. | R | C: Project Team, Business |  | Y | Business Requirements Document (BRD)
64 | Data Integration | Business Requirements Documents Creation | Create BRD Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR and upload to Sharepoint. | R | A: Project Team, Business |  | Y | Artifact Signoff Form (ASF) or ADR
65 | Data Integration | Gap Analysis | Perform Source to Target Gap Analysis to determine if all of the entities and attributes required are accounted for in UDW Base. | R | C: Database Analyst |  | Y | Map & Gap Template |  | Map and Gap COSMOS to DSS_Med Claim and Encounters
66 | Data Integration | Gap Analysis | Review Gap Analysis with the Domain Lead in order to gain agreement on any model changes. | R | C: Domain Lead, Julie Stoltz | Map & Gap Analysis | N
67 | Data Integration | Model Changes | Present to the Data Model Oversight Committee (DMOC) any changes that will take place to the Data Model. NOTE: This meeting must take place before the ALM ticket with the DBA Change Request occurs. Additional Review Board tasks are in discussion and will be added to this spreadsheet when approved. | R | R: Project Team, Domain Lead, Data Architect and Oversight Commett | Map & Gap Analysis | Y | Use the Data Model to look at the Changes and Definitions | * Data_Model_ Oversight_Process * DBA Engagement Policy
68 | Data Integration | Model Changes | Complete follow-ups identified at the DMOC meeting and proceed with analysis and modeling. | R | R: Data Architect | Map & Gap Analysis | Y | Update documents based on followups where applicable.
69 | Data Integration | Model Changes | Utilizing the Source to Target Gap Analysis document, collaborate with Data Architect to determine model changes - Draft Data Model. | R | R: Data Architect and other team members based on complexity | Map & Gap Analysis | Y | Draft Data Model
70 | Data Integration | Model Changes | The Database Architect will create ALM ticket with the DBA Change Request and the BA will update DBA Change Request for the modeling discussion. | R | R: Database Architect |  | Y | * ALM Ticket * DBA Change Request
71 | Data Integration | Model Changes | Update the Data Modeling Oversight Template located on the BA Sharepoint with the proposed changes to review. | R | R: Data Architect C: Project Team | * Map & Gap Analysis * Draft Data Model | Y | Data Modeling Oversight Template
72 | Data Integration | Model Changes (MOSI) | With any project, analysis will also need to be performed to remain in line with the Model Simplification Tables (MOSI). These are the tables in the Warehouse that contain the suffix "_F". If the project you are working on is adding or changing UDWBASE Tables/Attributes, new or existing MOSI tables will also need to be considered for UDWBASE. | R | R: Data Architect C: Project Team |  | Y
73 | Data Integration | Model Changes (MOSI) | When modifying original UDWBASE Tables/Attributes, utilize the MOSI Simplified Table Requirements Spreadsheet, determine if a table you are changing appears in the '3NF/Original Table' Column. If so, it will provide the Simplified Table or Semantic View (MOSI) in Column C. Consult the notes in the 'Comment on Any changes' Column to determine what needs to be updated for the MOSI Table and follow Tasks 66 through 70 for Model changes. | R | R: Data Architect C: Project Team |  | Y | *See Tasks 66 to 70 *MOSI Simplified Table Requirements
74 | Data Integration | Model Changes (MOSI) | When adding new Tables to UDWBASE, work through the same tasks as illustrated above Tasks 66 through 70 for Model changes. | R | R: Data Architect C: Project Team |  | Y | *See Tasks 66 to 70 *MOSI Simplified Table Requirements
75 | Data Integration | Model Changes | Any changes to UDW may affect Publication/Subscriptions. Perform analysis to determine if any existing Publications/Subscriptions will be impact. There are 19 Steps involved in the Pub Sub Impact Analysis. Please consult the UDW_Pub Sub Impact Process document. | R | C: Project Team | * Map & Gap Analysis * Query DPF Tables in UDWETLCNTLVIEW * P/S Mapping docs * P/S Technical Specs * P/S Extract SQL *ImpactAnalysis Review Board Checklist | Y | No Template - Follow Process Document and See Samples | * UDW_Pub Sub Impact Process * Pub Sub Impact Analysis * Post Pub Sub Impact Analysis | * PubSub_Impact Analysis_ALM16886 * PubSub_Impact_ Analysis_Comm_ALM16886 * PubSub_Impact Analysis_Comm_ALM17190 * PubSub_Impact Analysis_Mapping Docs_ALM17190
76 | Data Integration | Model Changes | Notify Domain Leads and End User of any Pub Sub Impacts. | R | C: Domain Lead, Julie Stoltz | P/S Impact Analysis | Y
77 | Data Integration | Model Changes | Any changes to UDW may affect Semantic Views. Perform analysis to determine if any existing Semantic Views will be impact. | R | C: Project Team | *Semantic View Specs located in the UDW Base Specification Documents Sharepoint | Y | No Template - Document Semantic View name, Spec Doc, Entity, Attribute, etc. | Planned for future
78 | Data Integration | Model Changes | Notify Domain Leads of any Semantic View Impacts. | R | C: Domain Lead, Julie Stoltz | P/S Impact Analysis | Y
79 | Data Integration | Model Changes | Present impacts and changes to the Data Model Oversight Committee (DMOC). | R | R: Project Team and Oversight Commett | * Map & Gap Analysis * P/S Impact Analysis | Y | Data Model
80 | Data Integration | Model Changes | Complete follow-ups identified at the DMOC meeting and proceed with analysis and modeling. | R | R: Data Architect | * Map & Gap Analysis * P/S Impact Analysis | Y | Update documents based on followups where applicable.
81 | Data Integration | Model Changes | Update DBA Change Request and ALM for the Logical Data Model. | R | I: Database Analyst |  | Y | DBA Change Request Template
82 | Data Integration | Model Changes | Perform BA checkout | R |  |  | Y | No Template - Document BA Test Cases and Expected Results.
83 | Data Integration | Functional Specification | Create Functional Specification to include: * Reference to Source to Target Mapping document * Reference to Semantic View document * Data loading/selection criteria information for first time historical data loads. * Data Security information * Any additional information pertaining to the project. Note: One or more functional specs may be required based on the scope of the project across domains, or how the work is broken down. | R |  | * High Level Design Documents * Data Models | Y | Functional Specification Template
84 | Data Integration | Functional Specification | Conduct review sessions with the Domain Leads and Project Team for Functional Specification document delivery and signoff. | R | C: Domain Leads, Project Team | Functional Specification Template | Y | Functional Specification Template
85 | Data Integration | Functional Specification | Create Functional Spec Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR. | R | A: Project Team |  | Y | Artifact Signoff Form (ASF) or ADR
86 | Data Integration | Functional Specification | Upload ASF and Functional Specification document to project Sharepoint. Inform Project Team. | R | I: Project Team |  | Y | No template - Email notification
87 | Data Integration | Source to Target Mapping | Create a copy of the mapping checklist and upload to your project sharepoint and Inform Project Team. Use this checklist as you proceed through the Source to Target Mapping activities. | R |  |  | Y | UDW BA Mapping -Checklist - Master
88 | Data Integration | Source to Target Mapping | Begin work on the Source to Target Mapping (STM) document once the data model is built including: * Table-File-Message * Table-File-Message Layout * Mapping * Transformation Rules * Primary Key Information * Any other information relevant to the project NOTE: If you are updating any existing mappings, refer to UDW Base Specification Document Sharepoint and follow the 'BA Standards_Document Updates' procedure. | R |  | * Map & Gap Analysis * Data Model | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE | * UDW BA Mapping - Overview * UDW BA Mapping - Match Rules (the rules) * Best Practices for Match Rules v1 (writing the rules) * Best Practices for Match Rules BA team (Overview) * BA Standards_Document Updates | STM_Dental Claim_SIH
89 | Data Integration | Source to Target Mapping | Complete first pass of mapping. | R |  |  | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE
90 | Data Integration | Source to Target Mapping | Complete all "Best Practices" items from the "UDW BA Mapping - Standard Rules" document | R |  | UDW BA Mapping - Standard Rules | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE | UDW BA Mapping - Standard Rules
91 | Data Integration | Source to Target Mapping | Complete all "Data Inspection" items from "UDW BA Mapping - Standard Rules" document | R |  | UDW BA Mapping - Standard Rules, Best Practices Tab - filter on Data Inspection | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE | UDW BA Mapping - Standard Rules
92 | Data Integration | Source to Target Mapping | Meet with Source SME's to understand any enriched data attributes. | R | C: Source SMEs | Source Documentation | N
93 | Data Integration | Source to Target Mapping | Review enrichment requirements with the Project Team to determine if current UDW enrichments will meet the business requirement or if new enrichments will need to be implemented in this mapping. NOTE: Depending on the type and complexity of the enrichment, a new mapping document and or functional specification may be required. | R | C: Project Team |  | Y | * UDW BA Mapping BASE_MAPPING_TEMPLATE *Functional Specification
94 | Data Integration | Source to Target Mapping | Collaborate with Database Architect and Project Team for any additional model changes - Repeat Tasks 66 to 82. | C | R: Database Architect C: Project Team |  | Y | See Tasks 66 to 82
95 | Data Integration | Source to Target Mapping | Conduct review sessions with the Domain Leads to work through mapping issues on the Source to Target Mapping document. | R | C: Domain Leads |  | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE
96 | Data Integration | Source to Target Mapping | Conduct review sessions with Project Team. | R | C: Project Team |  | Y | UDW BA Mapping BASE_MAPPING_TEMPLATE
97 | Data Integration | Source to Target Mapping | Create STM Artifact Signoff Form (ASF), obtain applicable signoffs or obtain signoff via ADR. | R | A: Project Team |  | Y | Artifact Signoff Form (ASF) or ADR
98 | Data Integration | Source to Target Mapping | Upload ASF and Source to Target Mapping document to project Sharepoint. Inform Project Team. | R | I: Project Team |  | Y | * Artifact Signoff Form (ASF) or ADR * UDW BA Mapping BASE_MAPPING_TEMPLATE
99 | Data Integration | Source to Target Mapping | Handoff Source to Target Mapping Document to ETL | R | I: ETL Team |  | Y | No template - Email notification
100 | Data Integration | Source to Target Mapping | Perform BA checkout once ETL work is completed. | R | C: ETL Team, Project Team |  | Y | Document BA Test Cases and Expected Results. See sample document |  | 3RDD_HHS_Extract_RXClaim_Iteration_Test_Cases
101 | Data Integration | Source to Target Mapping | If additional changes are required for the Data Model, Repeat Tasks 66 to 82. | R |  |  | Y | See Tasks 66 to 82
102 | Data Integration | Source to Target Mapping | If additional changes are required for the Mapping Document, Repeat Tasks 95 to 100. | R |  |  | Y | See Tasks 95 to 100 use sample document
103 | Data Integration | Data Quality | Engage with Data Quality Team to determine attributes/values that will require new data quality metrics or updates to existing metrics. | R | A: Data Quality Team |  | Y | * No template - Email notification of project * BA's will fill in Columns D - AB in the sample template |  | DQ_Msrmt_Req_2015_Q4_Combined_sample
104 | Data Integration | Reference Data | Document reference requirements, source feed or MRR. NOTE: Additional training will be available shortly. | R | C: MRR Administrator |  | Y |  | *MRR Sharepoint: http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Forms/AllItems.aspx?RootFolder=%2Fsites%2FA10%2F700%2F702%2F702%2E2%2FIntTm%2FDLi003%2FReference%20Data%20Management%20%28MRR%29&FolderCTID=0x0120009B8958B9E4C4AB49899CFB92E9ADDAD0&View={DD088E5B-9407-4183-B1FD-ADAA19ADCB4D} *UDW MRR Standard Work Package *Standards for UDW Reference Table Design
105 | Data Integration | MRR - New Physical Table | Create MRR Specification document for each structural change in the MR database (new table, change to existing table) | R | C: MRR Administrator | * Data Model *Source to Target Mapping document | Y | MRR Spec - Template
106 | Data Integration | MRR - New Physical Table | Create & submit Security Request Form | R | C: MRR Administrator |  | Y | The template to fill out is within SECURE | MRR-Security Request process for new MRR Tables
107 | Data Integration | MRR - New Physical Table | Create ALM Service Ticket for Teradata Development team to model and develop new tables - Attach MRR Spec document | R | C: MRR Administrator | MRR Specification Document | Y | ALM Service Ticket
108 | Data Integration | MRR - New Physical Table | Create ALM Service Ticket for the MRR Administrators to setup framework in MRRPROD and Initiate Requests with DB2 Team. Include: * 5 digit table code, as provided by Teradata resource * Attach MRR Spec document - MRR Admin will forward MRR Spec to Marylou Mousseau via email to secure DB2 modeling and development resources. | R | R: DB2 Team C: MRR Administrator | MRR Specification Document | Y | ALM Service Ticket
109 | Data Integration | MRR - New Physical Table | Once DB2 Table has been developed in MRRDEV, create ALM to forward MRR Specification to Tools Team for development | R | C: MRR Administrator | MRR Specification Document | Y | ALM Service Ticket
110 | Data Integration | MRR - New Physical Table | Test DMP/MRR User Interface functionality | R | C: MRR Administrator |  | N
111 | Data Integration | MRR - New Physical Table | Track ALMs through lifecycle | R | C: MRR Administrator |  | N
112 | Data Integration | MRR New Auto Reference Table Development | Create MRR Specs document for each structural change in the MRR database (new table, change to existing table) | R | C: MRR Administrator |  | Y | MRR Spec - Template
113 | Data Integration | MRR New Auto Reference Table Development | Create ALM Service Ticket for MRR Administrators to setup framework in MRRPROD. * Include 5 digit table code, as provided by Teradata resource * Attach MRR Specs document | R | R: MRR Administrator | MRR Specification Document | Y | ALM Service Ticket
114 | Data Integration | MRR New Auto Reference Table Development | Test DMP/MRR user interface functionality. | R | C: MRR Administrator |  | N
115 | Data Integration | MRR New Auto Reference Table Development | Track ALM through lifecycle | R | C: MRR Administrator |  | N
116 | Data Integration | Adding Data to MRR Tables | Gather values, descriptions from the source(s) | R | C: MRR Administrator |  | N
117 | Data Integration | Adding Data to MRR Tables | Add data via Import File or Manual Entry | R | C: MRR Administrator |  | Y | Import File Template | See MRR Import File Templates Folder on the MRR Sharepoint
118 | Data Integration | Adding Data to MRR Tables | Create MRR Log record | R | C: MRR Administrator |  | Y | No template - Found in the Data Maintenance Portal (DMP)
119 | Data Integration | Adding Data to MRR Tables | Request that the MRR Administrator to trigger the extracts to run to the necessary environments. | R | R: MRR Administrator |  | Y | No template - Email notification
120 | Data Integration | Semantic Views | Semantic Views are configured to support the reporting needs of the business. Each view displays relevant fields to support defined business needs. Attributes are organized to help support the business user. |  |  |  | N/A
121 | Data Integration | Semantic Views | Perform analysis and meet with Data Base Analysis and Customer to determine if there is a need for the creation of Semantic Views. | R | C: Data Base Analyst C: Customer |  | Y | Semantic View Sample layout
122 | Data Integration | Semantic Views | Collaborate with Database Architect and Project Team for any additional model changes if needed - Repeat Tasks 66 to 92. | C | R: Database Architect C: Project Team |  | Y | See Tasks 66 to 92
123 | Data Integration | Semantic Views | Prepare new Semantic View mappings where applicable - Repeat Tasks 95 to 100. | R | I: Data Base Analyst |  | Y | See Tasks 95 to 100 use sample document |  | Semantic View Sample layout
124 | Publication Subscription | Publication Subscription | A Publication Subscription is an extract sent to a customer on a scheduled basis. Data is usually extracted from UDW Base and in some cases from UDW Stage to fulfill the business requirements. Not all customers require extracts. | R | R: Project Team |  | N/A
125 | Publication Subscription | Publication Subscription | Meet with Source SME's to determine if there is a need for the creation of a Publication/Subscription. NOTE: Pub/Sub could be part of a DI Project or it could be a standalone project - pulling data from an acquired source or an intergrated source. Additional Review Board tasks are in discussion and will be added to this spreadsheet when approved. | R | R: Project Team |  | N
126 | Publication Subscription | Publication Subscription | Prepare new Publication Subscription mappings where applicable - Repeat Tasks 95 to 100. | R |  |  | Y | See Tasks 95 to 100 use sample document |  | PS_3RDD_Pharmacy Claim
127 | COGNOS BI Reporting | COGNOS BI Reporting | COGNOS is a web-based business intelligence solution which provides drag and drop functionality to create simple or highly complex queries and reports. COGNOS includes pre-build joins, so users no longer need to be SQL experts. Available views simplify the structure of data housed in UDW's Base environment.
128 | COGNOS BI Reporting | COGNOS BI Reporting | For any new Tables or Attributes that are added to the UDW Base Secure View, these same Tables and Attributes need to be added to the COGNOS Framework. Notify the COGNOS Team when this occurs: * Aggarwal, Nidhi nidhi.aggarwal1@optum.com (India - IST) OR * Bandaru, Swathi swathi_bandaru@optum.com (MN - CST) | R | R: COGNOS Team C: Project Team |  | Y | Provide DBA Change Request to the COGNOS Team
129 | Release Notes | Release Notes Creation | Release Notes should be started at the beginning of the project. As information becomes available, populate the Release Notes Template. This information is also used as the basis for the UAT Template, the Release Communication to the UDW User Community, and for the publication to the UDW Intranet. Create Release Notes information following the documented procedure located on the BA Sharepoint. | R | C: Project Team | * Project BRD * Mapping Documents * Functional Specs | N/A
130 | Release Notes | Release Notes Creation | Using the BA Release Notes Template, gather together information regarding: * Project Overview in Business Language (Non-Technical) * New/Modified/Deleted Tables and Attributes * Enriched data * Semantic View information * New source code information * Data Load cycles * Historical Data load | R | I: Project Team |  | Y | Release Notes Template_BA | * BA Release Notes Process * UDW Release Notes and UAT Process Overview
131 | Release Notes | Release Notes Creation | Review information with the Project Team and Domain SMEs for completeness. | R | I: Project Team |  | Y | Release Notes Template_BA
132 | Release Notes | Release Notes Creation | Upload to Project Sharepoint and to the Release Sharepoint and inform Release Notes Coordinator and Release Manager that the template is complete. | R | I: Release Notes Coordinator, Release Mgr. |  | Y | * Release Notes Template_BA * No template - Email notification
133 | Metadata Repository - See PNP_Metadata Repository Updates for when to complete tasks | Metadata Repository (MR) Updates | The UDW Metadata Repository houses all of the metadata about the UDW Database. The UDW Metadata Repository is updated with the monthly releases. For physical table/columns and semantic view/columns provides: *Table and Column definitions *Data Type & Length *Indexes (PK/FK) *Identify Table vs View *Business Join information For physical tables only, also provides: *Data Lineage *% Not Null/column/Source
134 | Metadata Repository | MR Definitions | For Physical Tables - in order to provide Table/Column definitions complete the DBA Change Request and forward in an ALM to the DA for upload to Erwin and then DA will forward to DBA for upload to Teradata DB Environments. Once OPS has given the confirmation that a Release is complete, the MR Team will scan the UDWBASESECUREVIEW DB to upload the definitions to the Metadata Repository. Follow standard process outlined in the PNP_Metadata Repository Updates | R | A: Data Architect, Database Analyst, Metadata Repository Team | *Model Integration Document (MID) *STM Mapping Document | Y | *DBA Change Request | *PNP_Metadata Repository Updates
135 | Metadata Repository | MR Definitions | For Semantic Views - in order to provide View/Column defintions complete the VMS Specification Document and forward in an ALM to the DBA for upload to the UDWBASESECUREVIEW Database Comments. Once OPS has given the confirmation that a Release is complete, the MR Team will scan the UDWBASESECUREVIEW DB to upload the definitions to the Metadata Repository. Follow standard process outlined in the PNP_Metadata Repository Updates. | R | A: Database Analyst, Metadata Repository Team | *VMS Template | Y | *VMS Mapping Document complete | *PNP_Metadata Repository Updates
136 | Metadata Repository | MR Data Lineage & % Not Null | Data Lineage provides information on the Source Table and Source Column for UDW Columns on Physical Tables and the UDW Transformation Rules. This information is entered on the Project Metadata Repository Input Spreadsheet (MRIS) from the STM Mapping document. % Not Null provides information by Source by Column the percentage of time this Column is populated by the Source. This process will now be run periodically (twice per year) outside of the Monthly Release Schedule. | I | R: OPS Team | *UDWBASESECUREVIEW DB | N | N/A | N/A
137 | Metadata Repository | MR Business Joins | Business Join information provides the UDW User with what Tables and Views can be joined when running their queries. The Project BA will enter this information on the Business Join Information Tab on the DBA Change Request and provide to the DBA for review. Once a Release is complete and these Joins have been moved to Production, the MR Team will scan the UDWBASESECUREVIEW DB to upload the Join information to the Metadata Repository. Follow standard process outlined in the PNP_Metadata Repository Updates. | R | A: Database Analyst | *Business Join Information | Y | *DBA Change Request | *PNP_Metadata Repository Updates
138 | Metadata Repository | MR Data Lineage | Once Object Deployment is complete, the Project BA will verify that all information on the Project MRIS is correct. There could be instances during a release that may cause tables/columns or data to be backed out of a release. If this is the case, the MRIS will need to be updated. This validation must take place before OPS runs the Bulk Upload to load the Data Lineage information to the Metadata Repository. | R | C: Database Analyst | *Confirmed Object Deployment | Y | *Project Metadata Repository Input Spreadsheet (MRIS) (WIP) | *PNP_Metadata Repository Updates
139 | Data Dictionary | Data Dictionary Creation | Once the DBA has completed work to move new objects to Production, the Release Notes Coordinator will request the running of the Data Dictionary Spreadsheet. Once the Metadata Repository process is running smoothly, the running of the Data Dictionary Spreadsheet will be decommissioned. | I | R: Release Notes Coordinator, Release Mgr. | *Confirmation from the DBA that all Release objects have been moved to Production | Y | No template - Email notification
140 | User Acceptance Testing | UAT Documentation | Prepare UAT Powerpoint Template to communicate to the UDW Test Group: * Project Overview * Any new/modified/deleted Tables and Attributes * Any enrichment information * Any Semantic View information * Specification documentation that may be helpful for testing purposes * Data available in the Test Environment * Any Query Criteria that may be helpful for testing purposes | R | I: Project Team | * Mapping Documents * Enrichment Functional Specs * Semantic View Specs * Security Functional Specs * Data Models * Process Specs * SQL Tips | Y | UDW_UAT_Source Domain - Template
141 | User Acceptance Testing | UAT Documentation | Review UAT Documentation with UDW UAT Lead and Project Team. | R | C: UAT Lead, Project Team | UDW UAT Source Domain Template | Y | UDW_UAT_Source Domain - Template |  | Sample_UDW_10042_OXF_NICE_Plan of Benefit_May UAT 202017.pptx
142 | User Acceptance Testing | UAT Documentation | BPMO will set up the UDW UAT Kickoff meeting to review UAT Documentation with the UDW Test Group. | R | I: UDW Test Group | UDW UAT Source Domain Template | Y | UDW_UAT_Source Domain - Template
143 | User Acceptance Testing | UAT Testing | While UAT Testing is in progress, the BPMO UAT Lead will conduct testing status update meetings throughout the UAT period. BA will be on hand to address any inquiries or UAT Tickets. | R/A | R: BPMO UAT Lead C: Project Team |  | N/A
144 | User Acceptance Testing | UAT Testing | All UAT issues are sent to the UAT Email Box. BA Lead (Either Project Lead BA or UAT Lead BA) will enter ALM Ticket and perform triage. If the ALM requires further analysis, a Project BA will be assigned for investigation. | R/A | I: Project Team |  | Y | UDW Release Notes and UAT Process Overview - for filling out ALM Ticket information
145 | User Acceptance Testing | UAT Testing | Once UAT Testing is complete, UAT Lead will obtain Signoff from Testers, complete ASF and upload to the project sharepoint or obtain signoff via ADR. | I | R: UAT Lead I: Project Team |  | Y | Artifact Signoff Form (ASF) or ADR
146 | Deployment | Pre-Deployment and Deployment Activities | Several activities take place to ensure that there is a smooth transfer of changes implemented to Production. | R | R: Project Team |  | N/A
147 | Deployment | Operations Readiness Checklist (ORC) Meeting | This is the handoff to the Operations Team regarding all aspects of the project and what is expected of the Operations Team once in Production. This meeting is held before the GATE meeting. The Project Manager will author the ORC and other project participants will provide input. * Project Overview * Changes to UDW Base/Mappings/Views/etc. * Review new Production Documentation and/or changes to existing Production Documentation * Any outstanding ALM's | C | R: Project Mgr. | Project Documentation | Y | Operations Readiness Checklist
148 | Deployment | GATE Meeting | This is the meeting that takes place prior to deployment to Production. Any projects that impact UDW BASE are presented to Department Leads for deployment approval. The UDW Project is presented by the Project Mgr. The Lead Project BA is expected to attend the GATE meeting to provide additional project clarification if needed. | C | R: Project Mgr. C: Project Team | * TRB * Implementation Doc * ORC * ORG Reviews * UAT * HPSM Chg Tkt | Y | Project Mgr adds the GATE Item to the GATE Agenda | Project Mgr. follows instructions in the GATE Email.
149 | Deployment | Knowledge Transfer Session | This is the meeting that takes place to provide information regarding the impacts to UDW Base to the UDW Domain Leads and Teams. Here the Lead BA and applicable Project BAs will present: * Project Overview * Changes to UDW Base/Mappings/Views/etc. * Review new Production Documentation and/or changes to existing Production Documentation * Any outstanding ALM's As part of Knowledge Transfer, the Knowldege Transfer Checklist and the Domain Overview should be completed and stored on the BA Function Sharepoint. | R | R: Lead BA, other Project BAs C: Domain Leads and Teams | Project Documentation | Y | *A Spreadsheet of information or Powerpoint may be provided by the Lead BA with input from other Project BA's if required. The UAT Kickoff PPT may also be used with some added technical details if necessary. *Knowledge Transfer Checklist *Domain One-Pager Document *Domain Overview *Domain ALM HPSM Open Items and FAQs |  | BA SME Claims KT Session - Pharmacy
150 | Deployment | Production Deployment | The Project Deployment Plan, created by the Project Mgr. with input from the Project Team, will be followed to implement changes to Production. Lead BA and applicable Project BAs will attend Deployment Check Point Meetings until deployment is complete to monitor and triage any issues that may occur. | R | R: Project Team | Project Deployment Plan | N
151 | Deployment | BA Checkout | Once Project changes have been completed to Production, applicable Project BAs will perform BA checkout. * Inform of any issues * Provide Checkout Signoff * Provide Checkout support to other Project Team members. | R | C: Project Team |  | Y | * ALM Service Ticket if applicable * No template - Signoff Email Notification | BA Standards_Production Checkout
152 | Data Acquisition/Data Integration | Change Request | A Change Request will be needed when: * Project Requirements change * Further analysis determines that the scope of the work is larger than anticipated during SOW or BRD estimate | R | R: Project Team |  | N/A
153 | Data Acquisition/Data Integration | Change Request | Project PM will create the Change Request with input from the Project Team. | C | R: Project Mgr. C: Project Team |  | Y | DMO Change Request Template
154 | Project Support | End User Community Project Review | End User Community Project Review may take place at the beginning of a project to inform the UDW User Community about the project, how it may impact them and give them time to react to changes that may need to occur in their processes. | R |  | * Business Value Document * Statement of Work * Agile Team Agreement | Y | UDW End User Community Project Review Template
155 | Project Support | End User Community Project Review | Prepare the Template as follows: NOTE: Remove all blue instruction notes from the final version. Slide 1: Cover Slide * Update Cover slide with Project Name, BA Name, Presentation Date Slide 2: Table of Contents * Do not change, add to or delete these bullet points Slide 3: Impact Assessment * Do not change anything on this slide, but use it as talking points to inform the audience why you are doing this review Slide 4: Business Overview * Provide an Executive Summary in business language terms. Slide 5: UDW Project Summary * Provide a high level summary of what UDW will create and delivery for this project Slide 6: UDW Project Details * Ensure that all detail impacts of your project are included on this slide. The list provided may not be all inclusive. Note: Additional information may be added to this Task as it becomes available. | R | C: Project Team | * Business Value Document * Statement of Work * Agile Team Agreement | Y | UDW End User Community Project Review Template |  | Sample_End User Community Project Review - PRJ113908 EHB Tagging

## Referenced Documents
Type | Document Name | Located At | Notes
Acquisition | Data Intake Checklist | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Data%20Intake%20Checklist.xlsx
Mapping | UDW BA Mapping - Checklist - Master | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20-%20Checklist%20-%20Master.xlsx
Mapping | Semantic View Sample layout | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Semantic%20View%20Sample%20layout.xlsx
Reference/ Training | UDW_PubSubImpactProcess | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW_PubSubImpactProcess.pptx
Mapping | UDW BA Mapping BASE_MAPPING_TEMPLATE_MEDCLM1 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20BASE_MAPPING_TEMPLATE_MEDCLM1.xlsm
Mapping | UDW BA Mapping BASE_MAPPING_TEMPLATE | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20BASE_MAPPING_TEMPLATE.xlsm
Mapping | UDW BA Mapping - Standard Rules | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20-%20Standard%20Rules.xls
Mapping | UDW BA Mapping - Match Rules | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20-%20Match%20Rules.xlsx
Acquisition | Data Intake Staging Process | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Data%20Intake%20Staging%20Process.vsd
Analysis Template | Data Lifecycle Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Data%20Lifecycle%20Template.doc
Data Discovery Questionnaire | Initial Data Sourcing Discussion Questions This document has more questions than the one in row 16. | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Initial%20Data%20Sourcing%20Discussion%20Questions.doc
Interface Agreement | Interface Agreement Process | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Interface%20Agreement%20Process.doc
Metadata Master | Metadata Master Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Metadata%20Master%20Template.xls
Metadata Master | MM Metadata Master Process | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/MM%20Metadata%20Master%20Process.ppt
Acquisition | UDW BA Data Discovery and Staging Training | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW%20BA%20Data%20Discovery%20and%20Staging%20Training.ppt
Reference/ Training | UDW Data Discovery Questionnaire Overview | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW%20Data%20Discovery%20Questionnaire%20Overview.ppt
Analysis Template | UDW Data Discovery Questionnaire | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW%20Data%20Discovery%20Questionnaire.xls
Reference/ Training | UDW Data Lifecycles | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW%20Data%20Lifecycles.ppt
Reference/ Training | Best Practices for Match Rules BA team | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Best%20Practices%20for%20Match%20Rules%20BA%20team.ppt
Reference/ Training | Best Practices for Match Rules | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Best%20Practices%20for%20Match%20Rules%20v%201.docx
Analysis Template | Map and Gap_Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Map%20and%20Gap_Template.xlsx
Reference/ Training | Data_Model_Oversight_Process | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20DA%20Data%20Model%20Oversight/Data_Model_Oversight_Process.pptx
Reference/ Training | DBA Engagement PolicyV4 0 (2) | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20DA%20Data%20Model%20Oversight/DBA%20Engagement%20Policy.doc
Analysis Template | UDW_Data_Model_Oversight_Committee (template) | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20DA%20Data%20Model%20Oversight/UDW_Data_Model_Oversight_Committee.xlsx
Analysis Template | Template_DBAChangeRequest | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Metadata%20Repository%20Update%20Process/Template_DBAChangeRequest.xlsx
Reference/ Training | Post Pub Sub Impact Analysis | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Post%20Pub%20Sub%20Impact%20Analysis.docx
Reference/ Training | IA-Redbook | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/IA-Redbook.pdf
Analysis Tracker | InfoAnalyzer - Profiled Data Files | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/InfoAnalyzer%20-%20Profiled%20Data%20Files.xlsx
Reference/ Training | Info_Analyzer_-_Quick_Start_Guide, 051915 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Info_Analyzer_-_Quick_Start_Guide,%20051915.doc
Analysis Tracker | Profiling Request Tracking | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Profiling%20Request%20Tracking.xlsx
Reference/ Training | Reference Data Management Sharepoint (MRR) | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Forms/AllItems.aspx?RootFolder=%2Fsites%2FA10%2F700%2F702%2F702%2E2%2FIntTm%2FDLi003%2FReference%20Data%20Management%20%28MRR%29&FolderCTID=0x0120009B8958B9E4C4AB49899CFB92E9ADDAD0&View={DD088E5B-9407-4183-B1FD-ADAA19ADCB4D}
Reference/ Training | BA Release Notes Process | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Release%20Notes%20Process%20and%20Templates/BA%20Process%20and%20Templates/BA%20Release%20Notes%20Process.xlsx
Analysis Template | Release Notes Template_BA | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Release%20Notes%20Process%20and%20Templates/BA%20Process%20and%20Templates/Release%20Notes%20Template_BA.xlsx
Reference/ Training | UDW BA Mapping - Overview | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20BA%20Mapping%20-%20Overview.ppt
Reference/ Training | PNP_Document_Updates (Name changed to 'BA Standards_Document Updates') | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Standards_Document_Updates.xlsx
Analysis Template | DataAnalysisResultsTEMPLATE v3.0 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/DataAnalysisResultsTEMPLATE%20v3.0.xlsx
Analysis Template | UDW_UAT_Source Domain - Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UAT%20Documentation/UDW_UAT_Source%20Domain%20-%20Template.pptx
Sample | BRD_4-68460 - VBC Measurement Enhancements | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/BRD_4-68460%20-%20VBC%20Measurement%20Enhancements.doc
Sample | SAR_DA0182 BRMS Data Feeds to UDW_BRS | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/BRS%20-%20Billing%20and%20Receivable%20Management%20System%20Solution/SAR_DA0182%20BRMS%20Data%20Feeds%20to%20UDW_BRS.doc
Sample | IA_4-68497_BRMS | http://optum200.optum.com/sites/A1/300/303/Collab/402.1/Forms/PubDocs.aspx?InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence&GroupString=%3B%23DA%3B%23IA%3B%23&IsGroupRender=TRUE | Stays on Interface Agreement Location
Sample | Map and Gap COSMOS to DSS_Med Claim and Encounters | http://optum200.optum.com/sites/A10/400/402/IntTm/PJ102i003/0009982%20UDW-400067417-ODM%20DSS%20Medical%20Claim%20and%20Encounters/4_Design/4.1_Funct_Specs/Map%20and%20Gap%20COSMOS%20to%20DSS%20_Med%20Claim%20and%20Encounters.xlsx | Stays on Project Location
Sample | DDQ_Revenue_ESB | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/ESB%20-%20eServices%20Billing/DDQ_Revenue_ESB.xls
Sample | LC_Provider Demographics_NDB | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/NDB%20-%20Network%20Data%20Bank/LC_Provider%20Demographics_NDB.doc
Reference/ Training | UDW Release Notes and UAT Process Overview | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/Release%20Notes%20Process%20and%20Templates/BA%20Process%20and%20Templates/UDW%20Release%20Notes%20and%20UAT%20Process%20Overview.pptx
Sample | MM_CDB | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/CDB%20-%20Consumer%20Database/MM_CDB.xls
Sample | DAR_Provider_HHR | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/HHR%20-%20Harken%20Health/DAR_Provider_HHR.xlsx
Sample | STM_Dental Claim_SIH | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi001/D_Claim%20Statistical/Dental%20Claim/STM_Dental%20Claim_SIH.xls
Sample | PS_3RDD_Pharmacy Claim | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi001/CD_Publication%20Subscription/3Rs/PS_3RDD_Pharmacy%20Claim.xls
Sample | UDW_R6_5_UAT_EBDS_Cust_PlanPolicy | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW_R6_5_UAT_EBDS_Cust_PlanPolicy.pptx
Analysis Template | MRR Spec - Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Reference%20Data%20Management%20(MRR)/MRR%20Table%20Specs%20-%20Physical/MRR%20Spec%20-%20Template.xlsx
Reference/ Training | MRR - Security Request process for new MRR Tables | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Reference%20Data%20Management%20(MRR)/MRR%20BA%20Resources/MRR%20-%20Security%20Request%20Process%20for%20New%20MRR%20Tables.docx
Analysis Template | DMO Change Request Template | http://optum200.optum.com/sites/A1/300/301/artifacts/DMO%20Change%20Request%20Template.docx | Stays on Framework site
Analysis Tracker | Master Out of Scope Tracking - after decision | http://optumdocs.optum.com/sites/UHA/UDW/UDW1/Retirement/PG102.007/Retirement%20Program/Strategic%20Guidance%20Council/Master%20Out%20of%20Scope%20Tracking%20-%20after%20decision.xlsx | Stays on Strategic Guidance Council site
Sample | DDQ_CDB Data Discussions | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi002/CDB%20-%20Consumer%20Database/DDQ_CDB%20Data%20Discussions.doc
Analysis Template | Artifact Signoff Form (ASF) | http://optum200.optum.com/sites/A1/300/301/artifacts/Artifact%20Signoff%20Form.doc | Stays on Framework site
Analysis Template | Submission Template for SGC Topics | http://optumdocs.optum.com/sites/UHA/UDW/UDW1/Retirement/PG102.007/Retirement%20Program/Strategic%20Guidance%20Council/Submission%20Template%20for%20SGC%20Topics.pptx | Stays on Strategic Guidance Council site
Analysis Template | Business Requirements Document Template | http://optum200.optum.com/sites/A1/300/301/artifacts/Business%20Requirements%20Document%20Template.doc | Stays on Framework site
Analysis Template | Functional Specification Document Template | http://optum200.optum.com/sites/A1/300/301/artifacts/Functional%20Specification%20Document%20Template.doc | Stays on Framework site
Analysis Template | Operations Readiness Checklist | http://optum200.optum.com/sites/A1/300/301/artifacts/Operations%20Readiness%20Checklist.xls | Stays on Framework site
Sample | DQ_Msrmt_Req_2015_Q4_Combined_sample | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/DQ_Msrmt_Req_2015_Q4_Combined_sample.xlsx
Sample | PubSub_ImpactAnalysis_Mapping Docs_ALM17190 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/PubSub_ImpactAnalysis_Mapping%20Docs_ALM17190.xlsx
Sample | PubSub_Impact_Analysis_Comm_ALM17190 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/PubSub_Impact_Analysis_Comm_ALM17190.docx
Sample | PubSub_ImpactAnalysis_ALM16886 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/PubSub_ImpactAnalysis_ALM16886.xlsx
Analysis Template | FS_COGNOS Framework 3R | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/FS_COGNOS%20Framework%203R.xls
Sample | PubSub_Impact_Analysis_Comm_ALM16886 | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/PubSub_Impact_Analysis_Comm_ALM16886.docx
Analysis Template | Knowledge Transfer Checklist | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Domain%20Overviews%20and%20Knowledge/Template_Knowledge%20Transfer%20Checklist.xlsx
Sample | BA SME Claims KT Session - Pharmacy | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Domain%20Overviews%20and%20Knowledge/Pharmacy%20Claim/KT_Pharmacy%20Claim.pptx
Reference/ Training | Standards for UDW Reference Table Design | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Standards%20for%20UDW%20Reference%20Table%20Design.docx
Reference/ Training | UDW MRR Standard Work Package | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/UDW%20MRR%20Standard%20Work%20Package.xlsx
Reference/ Training | Guidelines for metadata definitions | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Metadata%20Repository%20Update%20Process/Guidelines%20for%20Metadata%20Definitions.docx
Analysis Tracker | MOSI Simplified Table Requirements | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/MOSI%20Simplified%20Table%20Requirements.xlsx
Analysis Tracker | Domain Overviews | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Domain%20Overviews%20and%20Knowledge/Domain%20Overviews.xlsx
Analysis Tracker | Domain ALM HPSM Open Items and FAQs | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/Domain%20Overviews%20and%20Knowledge/Domain%20ALM%20HPSM%20Open%20Items%20and%20FAQs.xlsx
Reference/ Training | ImpactAnalysis Review Board Checklist | http://adr2.uhc.com/apps/Optum%20DM%20-%20UDW%20Portfolio/Shared%20Document/PubSub%20Impact%20Analysis/ImpactAnalysis%20Review%20Board%20Checklist.xlsx | Stays on PubSub Impact Analysis Site.
Reference/ Training | BA Standards_Production Checkout | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Standards_Production%20Checkout.xlsx
Reference/ Training | Global IDs Tips and Tricks | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Global%20IDs-%20Tips%20and%20Tricks.docx
Reference/ Training | Global IDs-_Quick_Start_Guide | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Global%20IDs-%20Quick_Start_Guide.doc
Reference/ Training | Profiling Request Tracking - Global IDs | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Work%20Breakdown%20Structure/Supporting%20Documents%20not%20in%20other%20BA%20Admin%20locations/Global%20IDs-%20Profiling%20Request%20Tracking.xlsx
Reference/ Training | PNP_Metadata Repository Updates | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Metadata%20Repository%20Update%20Process/PNP_Metadata%20Repository%20Updates.xlsx
Analysis Template | Template_Project Metadata Repository Input Spreadsheet | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/BA%20Metadata%20Repository%20Update%20Process/Template_Project%20Metadata%20Repository%20Input%20Spreadsheet.xlsx
Analysis Template | UDW End User Community Project Review Template | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20End%20User%20Community%20Project%20Review/UDW_End_User_Community_Project_Review_Template.pptx
Sample | Sample_End User Community Project Review - PRJ113908 EHB Tagging | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UDW%20End%20User%20Community%20Project%20Review/Sample_End%20User%20Community%20Project%20Review%20-%20PRJ113908%20EHB%20Tagging.pptx
Sample | Sample_UDW_10042_OXF_NICE_Plan of Benefit_May UAT 202017.pptx | http://optum200.optum.com/sites/A10/700/702/702.2/IntTm/DLi003/BA%20Standards%20and%20Process/UAT%20Documentation/Sample_UDW_10042_OXF_NICE_Plan%20of%20Benefit_May%20UAT%202017.pptx